Monitoring and assessment - 2026

Sebastopol Primary School (1167)

Submitted for review by Kane Tolliday (School Principal) on 24 February, 2026 at 02:32 PM
Endorsed by Anne Gawith (Senior Education Improvement Leader) on 04 March, 2026 at 07:37 AM
Term 2 Monitoring submitted by Kane Tolliday (School Principal) on 24 June, 2026 at 02:01 PM

Monitoring and assessment - 2026

Term 1 monitoring (optional)

| ### Goal 1 | To improve student learning outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 1.c | Build staff capability to analyse and use learning and wellbeing data to accurately determine student’s needs |  |  |
| Actions | Build a data-driven culture by providing targeted professional development, implementing consistent assessment and wellbeing tracking tools, facilitating regular data review meetings, and supporting teachers through coaching and collaboration to use insights for informed instruction and student support. |  |  |
| Delivery of the annual actions for this KIS |  |  |  |
| Evidence of change | -Targeted Professional Learning: Provide professional development for teachers and leadership focused on data literacy, assessment interpretation, and wellbeing monitoring to build staff capability in analysing and using student data. - Expected Staff Outcomes: Teachers will demonstrate increased knowledge and skills in interpreting data, making evidence-based decisions, and applying differentiated strategies to support student learning and wellbeing. - Structured Data Meetings: Embed regular team and year-level meetings with agendas, minutes, and action plans to collaboratively identify student needs and plan interventions. - Consistent Assessment & Tracking Tools: Use platforms and tools such as Essential Assessment, PAT, Dibels, SPAKLE online tracking, internal School Tracking Documents, and Compass to collect, monitor, and report on student progress. - Data-Informed Planning: Teachers will routinely integrate data into lesson planning, make timely instructional adjustments, and provide targeted support for individual and group student needs. - Ongoing Coaching & Peer Support: Implement coaching, peer observations, and PLC reflections to reinforce collaborative decision-making, evidence-based practices, and a school-wide culture of data-informed practice. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Professional Learning & Training • Attendance records from data literacy or assessment-focused professional development sessions. • Workshop agendas, presentations, and resources showing the focus on interpreting learning and wellbeing data. • Teacher reflections or feedback forms demonstrating improved understanding of data use. | Leadership team | -1% |
| Task 2 | Structured Data Meetings • Meeting agendas and minutes documenting discussion of student data and decisions about targeted support. • Action plans created from data discussions identifying student learning and wellbeing needs. • Records showing follow-up on agreed strategies and interventions. | Leadership team | -1% |
| Task 3 | Assessment & Tracking Tools • Reports from platforms (e.g., Essential Assessment, Compass, NAPLAN, or internal tracking spreadsheets) showing student performance and wellbeing trends. • Evidence of consistent entry of assessment and wellbeing data by teachers. • Dashboards or visual summaries used to inform teaching practice. | Teacher(s) Leadership team | -1% |
| Task 4 | Data-Informed Planning • Lesson plans and unit plans explicitly linked to student data and differentiated strategies. • Examples of interventions or programs implemented in response to data analysis. • Evidence of student progress monitored over time using formative and summative assessments | Teacher(s) | -1% |
| Task 5 | Ongoing Coaching & Peer Support • Coaching logs showing sessions focused on interpreting and applying data. • Peer observation notes or PLC reflections highlighting the use of data to inform instruction. • Staff surveys or feedback demonstrating increased confidence in using data to identify student needs. | Teacher(s) Leadership team | -1% |

| ### Goal 2 | To improve student wellbeing outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 2.b | Review and embed a whole school positive approach to wellbeing. |  |  |
| Actions | Strengthen Sebastopol Primary School’s whole-school wellbeing approach by refining documentation, systems, and processes, enhancing the Wellbeing Hub, implementing Positive Classroom Management Strategies with ongoing professional learning, clarifying wellbeing team roles, and using student data to guide timely, targeted support and reintegration strategies. |  |  |
| Delivery of the annual actions for this KIS |  |  |  |
| Evidence of change | - Reduce behaviour referrals and student suspensions. - Increase positive outcomes in the Attitudes to School Survey. - Ensure consistent implementation and regular review of student support plans, including Individual Education Plans, Behaviour Support Plans and Safety Plans. - Fully implement the Positive Classroom Management Strategies, including refinement of the Behaviour Matrix and Behaviour Flowcharts. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Develop clear role descriptions for Wellbeing Team members. | Principal Learning specialist(s) Mental health and wellbeing leader Disability inclusion coordinator | -1% |
| Task 2 | Implement PCMS peer observations across Terms 2, 3 and 4. | Learning specialist(s) Teacher(s) Principal | -1% |
| Task 3 | Refresh the Wellbeing Hub and clarify associated expectations. | All staff Learning specialist(s) Mental health and wellbeing leader Principal | -1% |
| Task 4 | Update student support plans to align with Department of Education requirements. | Learning specialist(s) | -1% |
| Task 5 | Establish a structured approach and clear expectations for school-wide student surveys to ensure consistent and reliable data collection. | Leadership team Teacher(s) | -1% |

Monitoring and assessment - 2026

Mid-year monitoring

| ### Goal 1 | To improve student learning outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 1.c | Build staff capability to analyse and use learning and wellbeing data to accurately determine student’s needs |  |  |
| Actions | Build a data-driven culture by providing targeted professional development, implementing consistent assessment and wellbeing tracking tools, facilitating regular data review meetings, and supporting teachers through coaching and collaboration to use insights for informed instruction and student support. |  |  |
| Delivery of the annual actions for this KIS | Completed |  |  |
| Evidence of change | -Targeted Professional Learning: Provide professional development for teachers and leadership focused on data literacy, assessment interpretation, and wellbeing monitoring to build staff capability in analysing and using student data. - Expected Staff Outcomes: Teachers will demonstrate increased knowledge and skills in interpreting data, making evidence-based decisions, and applying differentiated strategies to support student learning and wellbeing. - Structured Data Meetings: Embed regular team and year-level meetings with agendas, minutes, and action plans to collaboratively identify student needs and plan interventions. - Consistent Assessment & Tracking Tools: Use platforms and tools such as Essential Assessment, PAT, Dibels, SPAKLE online tracking, internal School Tracking Documents, and Compass to collect, monitor, and report on student progress. - Data-Informed Planning: Teachers will routinely integrate data into lesson planning, make timely instructional adjustments, and provide targeted support for individual and group student needs. - Ongoing Coaching & Peer Support: Implement coaching, peer observations, and PLC reflections to reinforce collaborative decision-making, evidence-based practices, and a school-wide culture of data-informed practice. |  |  |
| Progress of evidence of change for this KIS | Some evidence of change observed |  |  |
| Enablers | Sufficient budget Sufficient time allocated The school was able to prioritise well |  |  |
| Barriers | Time constraints Workforce capability |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Professional Learning & Training • Attendance records from data literacy or assessment-focused professional development sessions. • Workshop agendas, presentations, and resources showing the focus on interpreting learning and wellbeing data. • Teacher reflections or feedback forms demonstrating improved understanding of data use. | Leadership team | 50% |
| Task 2 | Structured Data Meetings • Meeting agendas and minutes documenting discussion of student data and decisions about targeted support. • Action plans created from data discussions identifying student learning and wellbeing needs. • Records showing follow-up on agreed strategies and interventions. | Leadership team | 50% |
| Task 3 | Assessment & Tracking Tools • Reports from platforms (e.g., Essential Assessment, Compass, NAPLAN, or internal tracking spreadsheets) showing student performance and wellbeing trends. • Evidence of consistent entry of assessment and wellbeing data by teachers. • Dashboards or visual summaries used to inform teaching practice. | Teacher(s) Leadership team | 50% |
| Task 4 | Data-Informed Planning • Lesson plans and unit plans explicitly linked to student data and differentiated strategies. • Examples of interventions or programs implemented in response to data analysis. • Evidence of student progress monitored over time using formative and summative assessments | Teacher(s) | 50% |
| Task 5 | Ongoing Coaching & Peer Support • Coaching logs showing sessions focused on interpreting and applying data. • Peer observation notes or PLC reflections highlighting the use of data to inform instruction. • Staff surveys or feedback demonstrating increased confidence in using data to identify student needs. | Teacher(s) Leadership team | 50% |

| ### Goal 2 | To improve student wellbeing outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 2.b | Review and embed a whole school positive approach to wellbeing. |  |  |
| Actions | Strengthen Sebastopol Primary School’s whole-school wellbeing approach by refining documentation, systems, and processes, enhancing the Wellbeing Hub, implementing Positive Classroom Management Strategies with ongoing professional learning, clarifying wellbeing team roles, and using student data to guide timely, targeted support and reintegration strategies. |  |  |
| Delivery of the annual actions for this KIS | Completed |  |  |
| Evidence of change | - Reduce behaviour referrals and student suspensions. - Increase positive outcomes in the Attitudes to School Survey. - Ensure consistent implementation and regular review of student support plans, including Individual Education Plans, Behaviour Support Plans and Safety Plans. - Fully implement the Positive Classroom Management Strategies, including refinement of the Behaviour Matrix and Behaviour Flowcharts. |  |  |
| Progress of evidence of change for this KIS | All expected evidence of change observed |  |  |
| Enablers | Sufficient budget Access to resources/programs Sufficient time allocated Staff capability and consistency of practice Positive staff culture and readiness for change |  |  |
| Barriers | Workforce capability |  |  |
| OPTIONAL: Upload evidence | - SPS Mid Year Monitoring notes.docx (0.22 MB) |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Develop clear role descriptions for Wellbeing Team members. | Principal Learning specialist(s) Mental health and wellbeing leader Disability inclusion coordinator | 50% |
| Task 2 | Implement PCMS peer observations across Terms 2, 3 and 4. | Learning specialist(s) Teacher(s) Principal | 100% |
| Task 3 | Refresh the Wellbeing Hub and clarify associated expectations. | All staff Learning specialist(s) Mental health and wellbeing leader Principal | 100% |
| Task 4 | Update student support plans to align with Department of Education requirements. | Learning specialist(s) | 50% |
| Task 5 | Establish a structured approach and clear expectations for school-wide student surveys to ensure consistent and reliable data collection. | Leadership team Teacher(s) | 50% |

Monitoring and assessment - 2026

Term 3 monitoring (optional)

| ### Goal 1 | To improve student learning outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 1.c | Build staff capability to analyse and use learning and wellbeing data to accurately determine student’s needs |  |  |
| Actions | Build a data-driven culture by providing targeted professional development, implementing consistent assessment and wellbeing tracking tools, facilitating regular data review meetings, and supporting teachers through coaching and collaboration to use insights for informed instruction and student support. |  |  |
| Delivery of the annual actions for this KIS | Completed |  |  |
| Evidence of change | -Targeted Professional Learning: Provide professional development for teachers and leadership focused on data literacy, assessment interpretation, and wellbeing monitoring to build staff capability in analysing and using student data. - Expected Staff Outcomes: Teachers will demonstrate increased knowledge and skills in interpreting data, making evidence-based decisions, and applying differentiated strategies to support student learning and wellbeing. - Structured Data Meetings: Embed regular team and year-level meetings with agendas, minutes, and action plans to collaboratively identify student needs and plan interventions. - Consistent Assessment & Tracking Tools: Use platforms and tools such as Essential Assessment, PAT, Dibels, SPAKLE online tracking, internal School Tracking Documents, and Compass to collect, monitor, and report on student progress. - Data-Informed Planning: Teachers will routinely integrate data into lesson planning, make timely instructional adjustments, and provide targeted support for individual and group student needs. - Ongoing Coaching & Peer Support: Implement coaching, peer observations, and PLC reflections to reinforce collaborative decision-making, evidence-based practices, and a school-wide culture of data-informed practice. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Professional Learning & Training • Attendance records from data literacy or assessment-focused professional development sessions. • Workshop agendas, presentations, and resources showing the focus on interpreting learning and wellbeing data. • Teacher reflections or feedback forms demonstrating improved understanding of data use. | Leadership team | 50% |
| Task 2 | Structured Data Meetings • Meeting agendas and minutes documenting discussion of student data and decisions about targeted support. • Action plans created from data discussions identifying student learning and wellbeing needs. • Records showing follow-up on agreed strategies and interventions. | Leadership team | 50% |
| Task 3 | Assessment & Tracking Tools • Reports from platforms (e.g., Essential Assessment, Compass, NAPLAN, or internal tracking spreadsheets) showing student performance and wellbeing trends. • Evidence of consistent entry of assessment and wellbeing data by teachers. • Dashboards or visual summaries used to inform teaching practice. | Teacher(s) Leadership team | 50% |
| Task 4 | Data-Informed Planning • Lesson plans and unit plans explicitly linked to student data and differentiated strategies. • Examples of interventions or programs implemented in response to data analysis. • Evidence of student progress monitored over time using formative and summative assessments | Teacher(s) | 50% |
| Task 5 | Ongoing Coaching & Peer Support • Coaching logs showing sessions focused on interpreting and applying data. • Peer observation notes or PLC reflections highlighting the use of data to inform instruction. • Staff surveys or feedback demonstrating increased confidence in using data to identify student needs. | Teacher(s) Leadership team | 50% |

| ### Goal 2 | To improve student wellbeing outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 2.b | Review and embed a whole school positive approach to wellbeing. |  |  |
| Actions | Strengthen Sebastopol Primary School’s whole-school wellbeing approach by refining documentation, systems, and processes, enhancing the Wellbeing Hub, implementing Positive Classroom Management Strategies with ongoing professional learning, clarifying wellbeing team roles, and using student data to guide timely, targeted support and reintegration strategies. |  |  |
| Delivery of the annual actions for this KIS | Completed |  |  |
| Evidence of change | - Reduce behaviour referrals and student suspensions. - Increase positive outcomes in the Attitudes to School Survey. - Ensure consistent implementation and regular review of student support plans, including Individual Education Plans, Behaviour Support Plans and Safety Plans. - Fully implement the Positive Classroom Management Strategies, including refinement of the Behaviour Matrix and Behaviour Flowcharts. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Develop clear role descriptions for Wellbeing Team members. | Principal Learning specialist(s) Mental health and wellbeing leader Disability inclusion coordinator | 50% |
| Task 2 | Implement PCMS peer observations across Terms 2, 3 and 4. | Learning specialist(s) Teacher(s) Principal | 100% |
| Task 3 | Refresh the Wellbeing Hub and clarify associated expectations. | All staff Learning specialist(s) Mental health and wellbeing leader Principal | 100% |
| Task 4 | Update student support plans to align with Department of Education requirements. | Learning specialist(s) | 50% |
| Task 5 | Establish a structured approach and clear expectations for school-wide student surveys to ensure consistent and reliable data collection. | Leadership team Teacher(s) | 50% |

Monitoring and assessment - 2026

End-of-year monitoring

| ### Goal 1 | To improve student learning outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 1.c | Build staff capability to analyse and use learning and wellbeing data to accurately determine student’s needs |  |  |
| Actions | Build a data-driven culture by providing targeted professional development, implementing consistent assessment and wellbeing tracking tools, facilitating regular data review meetings, and supporting teachers through coaching and collaboration to use insights for informed instruction and student support. |  |  |
| Delivery of the annual actions for this KIS | Completed |  |  |
| Evidence of change | -Targeted Professional Learning: Provide professional development for teachers and leadership focused on data literacy, assessment interpretation, and wellbeing monitoring to build staff capability in analysing and using student data. - Expected Staff Outcomes: Teachers will demonstrate increased knowledge and skills in interpreting data, making evidence-based decisions, and applying differentiated strategies to support student learning and wellbeing. - Structured Data Meetings: Embed regular team and year-level meetings with agendas, minutes, and action plans to collaboratively identify student needs and plan interventions. - Consistent Assessment & Tracking Tools: Use platforms and tools such as Essential Assessment, PAT, Dibels, SPAKLE online tracking, internal School Tracking Documents, and Compass to collect, monitor, and report on student progress. - Data-Informed Planning: Teachers will routinely integrate data into lesson planning, make timely instructional adjustments, and provide targeted support for individual and group student needs. - Ongoing Coaching & Peer Support: Implement coaching, peer observations, and PLC reflections to reinforce collaborative decision-making, evidence-based practices, and a school-wide culture of data-informed practice. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Professional Learning & Training • Attendance records from data literacy or assessment-focused professional development sessions. • Workshop agendas, presentations, and resources showing the focus on interpreting learning and wellbeing data. • Teacher reflections or feedback forms demonstrating improved understanding of data use. | Leadership team | 50% |
| Task 2 | Structured Data Meetings • Meeting agendas and minutes documenting discussion of student data and decisions about targeted support. • Action plans created from data discussions identifying student learning and wellbeing needs. • Records showing follow-up on agreed strategies and interventions. | Leadership team | 50% |
| Task 3 | Assessment & Tracking Tools • Reports from platforms (e.g., Essential Assessment, Compass, NAPLAN, or internal tracking spreadsheets) showing student performance and wellbeing trends. • Evidence of consistent entry of assessment and wellbeing data by teachers. • Dashboards or visual summaries used to inform teaching practice. | Teacher(s) Leadership team | 50% |
| Task 4 | Data-Informed Planning • Lesson plans and unit plans explicitly linked to student data and differentiated strategies. • Examples of interventions or programs implemented in response to data analysis. • Evidence of student progress monitored over time using formative and summative assessments | Teacher(s) | 50% |
| Task 5 | Ongoing Coaching & Peer Support • Coaching logs showing sessions focused on interpreting and applying data. • Peer observation notes or PLC reflections highlighting the use of data to inform instruction. • Staff surveys or feedback demonstrating increased confidence in using data to identify student needs. | Teacher(s) Leadership team | 50% |

| ### Goal 2 | To improve student wellbeing outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 2.b | Review and embed a whole school positive approach to wellbeing. |  |  |
| Actions | Strengthen Sebastopol Primary School’s whole-school wellbeing approach by refining documentation, systems, and processes, enhancing the Wellbeing Hub, implementing Positive Classroom Management Strategies with ongoing professional learning, clarifying wellbeing team roles, and using student data to guide timely, targeted support and reintegration strategies. |  |  |
| Delivery of the annual actions for this KIS | Completed |  |  |
| Evidence of change | - Reduce behaviour referrals and student suspensions. - Increase positive outcomes in the Attitudes to School Survey. - Ensure consistent implementation and regular review of student support plans, including Individual Education Plans, Behaviour Support Plans and Safety Plans. - Fully implement the Positive Classroom Management Strategies, including refinement of the Behaviour Matrix and Behaviour Flowcharts. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Develop clear role descriptions for Wellbeing Team members. | Principal Learning specialist(s) Mental health and wellbeing leader Disability inclusion coordinator | 50% |
| Task 2 | Implement PCMS peer observations across Terms 2, 3 and 4. | Learning specialist(s) Teacher(s) Principal | 100% |
| Task 3 | Refresh the Wellbeing Hub and clarify associated expectations. | All staff Learning specialist(s) Mental health and wellbeing leader Principal | 100% |
| Task 4 | Update student support plans to align with Department of Education requirements. | Learning specialist(s) | 50% |
| Task 5 | Establish a structured approach and clear expectations for school-wide student surveys to ensure consistent and reliable data collection. | Leadership team Teacher(s) | 50% |

| ### Future planning |  |
| --- | --- |

Monitoring and assessment - 2026

Mid Term 1 monitoring

| ### Goal 1 | To improve student learning outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 1.c | Build staff capability to analyse and use learning and wellbeing data to accurately determine student’s needs |  |  |
| Actions | Build a data-driven culture by providing targeted professional development, implementing consistent assessment and wellbeing tracking tools, facilitating regular data review meetings, and supporting teachers through coaching and collaboration to use insights for informed instruction and student support. |  |  |
| Delivery of the annual actions for this KIS |  |  |  |
| Evidence of change | -Targeted Professional Learning: Provide professional development for teachers and leadership focused on data literacy, assessment interpretation, and wellbeing monitoring to build staff capability in analysing and using student data. - Expected Staff Outcomes: Teachers will demonstrate increased knowledge and skills in interpreting data, making evidence-based decisions, and applying differentiated strategies to support student learning and wellbeing. - Structured Data Meetings: Embed regular team and year-level meetings with agendas, minutes, and action plans to collaboratively identify student needs and plan interventions. - Consistent Assessment & Tracking Tools: Use platforms and tools such as Essential Assessment, PAT, Dibels, SPAKLE online tracking, internal School Tracking Documents, and Compass to collect, monitor, and report on student progress. - Data-Informed Planning: Teachers will routinely integrate data into lesson planning, make timely instructional adjustments, and provide targeted support for individual and group student needs. - Ongoing Coaching & Peer Support: Implement coaching, peer observations, and PLC reflections to reinforce collaborative decision-making, evidence-based practices, and a school-wide culture of data-informed practice. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Professional Learning & Training • Attendance records from data literacy or assessment-focused professional development sessions. • Workshop agendas, presentations, and resources showing the focus on interpreting learning and wellbeing data. • Teacher reflections or feedback forms demonstrating improved understanding of data use. | Leadership team | -1% |
| Task 2 | Structured Data Meetings • Meeting agendas and minutes documenting discussion of student data and decisions about targeted support. • Action plans created from data discussions identifying student learning and wellbeing needs. • Records showing follow-up on agreed strategies and interventions. | Leadership team | -1% |
| Task 3 | Assessment & Tracking Tools • Reports from platforms (e.g., Essential Assessment, Compass, NAPLAN, or internal tracking spreadsheets) showing student performance and wellbeing trends. • Evidence of consistent entry of assessment and wellbeing data by teachers. • Dashboards or visual summaries used to inform teaching practice. | Teacher(s) Leadership team | -1% |
| Task 4 | Data-Informed Planning • Lesson plans and unit plans explicitly linked to student data and differentiated strategies. • Examples of interventions or programs implemented in response to data analysis. • Evidence of student progress monitored over time using formative and summative assessments | Teacher(s) | -1% |
| Task 5 | Ongoing Coaching & Peer Support • Coaching logs showing sessions focused on interpreting and applying data. • Peer observation notes or PLC reflections highlighting the use of data to inform instruction. • Staff surveys or feedback demonstrating increased confidence in using data to identify student needs. | Teacher(s) Leadership team | -1% |

| ### Goal 2 | To improve student wellbeing outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 2.b | Review and embed a whole school positive approach to wellbeing. |  |  |
| Actions | Strengthen Sebastopol Primary School’s whole-school wellbeing approach by refining documentation, systems, and processes, enhancing the Wellbeing Hub, implementing Positive Classroom Management Strategies with ongoing professional learning, clarifying wellbeing team roles, and using student data to guide timely, targeted support and reintegration strategies. |  |  |
| Delivery of the annual actions for this KIS |  |  |  |
| Evidence of change | - Reduce behaviour referrals and student suspensions. - Increase positive outcomes in the Attitudes to School Survey. - Ensure consistent implementation and regular review of student support plans, including Individual Education Plans, Behaviour Support Plans and Safety Plans. - Fully implement the Positive Classroom Management Strategies, including refinement of the Behaviour Matrix and Behaviour Flowcharts. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Develop clear role descriptions for Wellbeing Team members. | Principal Learning specialist(s) Mental health and wellbeing leader Disability inclusion coordinator | -1% |
| Task 2 | Implement PCMS peer observations across Terms 2, 3 and 4. | Learning specialist(s) Teacher(s) Principal | -1% |
| Task 3 | Refresh the Wellbeing Hub and clarify associated expectations. | All staff Learning specialist(s) Mental health and wellbeing leader Principal | -1% |
| Task 4 | Update student support plans to align with Department of Education requirements. | Learning specialist(s) | -1% |
| Task 5 | Establish a structured approach and clear expectations for school-wide student surveys to ensure consistent and reliable data collection. | Leadership team Teacher(s) | -1% |

Monitoring and assessment - 2026

Mid Term 2 monitoring

| ### Goal 1 | To improve student learning outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 1.c | Build staff capability to analyse and use learning and wellbeing data to accurately determine student’s needs |  |  |
| Actions | Build a data-driven culture by providing targeted professional development, implementing consistent assessment and wellbeing tracking tools, facilitating regular data review meetings, and supporting teachers through coaching and collaboration to use insights for informed instruction and student support. |  |  |
| Delivery of the annual actions for this KIS |  |  |  |
| Evidence of change | -Targeted Professional Learning: Provide professional development for teachers and leadership focused on data literacy, assessment interpretation, and wellbeing monitoring to build staff capability in analysing and using student data. - Expected Staff Outcomes: Teachers will demonstrate increased knowledge and skills in interpreting data, making evidence-based decisions, and applying differentiated strategies to support student learning and wellbeing. - Structured Data Meetings: Embed regular team and year-level meetings with agendas, minutes, and action plans to collaboratively identify student needs and plan interventions. - Consistent Assessment & Tracking Tools: Use platforms and tools such as Essential Assessment, PAT, Dibels, SPAKLE online tracking, internal School Tracking Documents, and Compass to collect, monitor, and report on student progress. - Data-Informed Planning: Teachers will routinely integrate data into lesson planning, make timely instructional adjustments, and provide targeted support for individual and group student needs. - Ongoing Coaching & Peer Support: Implement coaching, peer observations, and PLC reflections to reinforce collaborative decision-making, evidence-based practices, and a school-wide culture of data-informed practice. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Professional Learning & Training • Attendance records from data literacy or assessment-focused professional development sessions. • Workshop agendas, presentations, and resources showing the focus on interpreting learning and wellbeing data. • Teacher reflections or feedback forms demonstrating improved understanding of data use. | Leadership team | -1% |
| Task 2 | Structured Data Meetings • Meeting agendas and minutes documenting discussion of student data and decisions about targeted support. • Action plans created from data discussions identifying student learning and wellbeing needs. • Records showing follow-up on agreed strategies and interventions. | Leadership team | -1% |
| Task 3 | Assessment & Tracking Tools • Reports from platforms (e.g., Essential Assessment, Compass, NAPLAN, or internal tracking spreadsheets) showing student performance and wellbeing trends. • Evidence of consistent entry of assessment and wellbeing data by teachers. • Dashboards or visual summaries used to inform teaching practice. | Teacher(s) Leadership team | -1% |
| Task 4 | Data-Informed Planning • Lesson plans and unit plans explicitly linked to student data and differentiated strategies. • Examples of interventions or programs implemented in response to data analysis. • Evidence of student progress monitored over time using formative and summative assessments | Teacher(s) | -1% |
| Task 5 | Ongoing Coaching & Peer Support • Coaching logs showing sessions focused on interpreting and applying data. • Peer observation notes or PLC reflections highlighting the use of data to inform instruction. • Staff surveys or feedback demonstrating increased confidence in using data to identify student needs. | Teacher(s) Leadership team | -1% |

| ### Goal 2 | To improve student wellbeing outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 2.b | Review and embed a whole school positive approach to wellbeing. |  |  |
| Actions | Strengthen Sebastopol Primary School’s whole-school wellbeing approach by refining documentation, systems, and processes, enhancing the Wellbeing Hub, implementing Positive Classroom Management Strategies with ongoing professional learning, clarifying wellbeing team roles, and using student data to guide timely, targeted support and reintegration strategies. |  |  |
| Delivery of the annual actions for this KIS |  |  |  |
| Evidence of change | - Reduce behaviour referrals and student suspensions. - Increase positive outcomes in the Attitudes to School Survey. - Ensure consistent implementation and regular review of student support plans, including Individual Education Plans, Behaviour Support Plans and Safety Plans. - Fully implement the Positive Classroom Management Strategies, including refinement of the Behaviour Matrix and Behaviour Flowcharts. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Develop clear role descriptions for Wellbeing Team members. | Principal Learning specialist(s) Mental health and wellbeing leader Disability inclusion coordinator | -1% |
| Task 2 | Implement PCMS peer observations across Terms 2, 3 and 4. | Learning specialist(s) Teacher(s) Principal | -1% |
| Task 3 | Refresh the Wellbeing Hub and clarify associated expectations. | All staff Learning specialist(s) Mental health and wellbeing leader Principal | -1% |
| Task 4 | Update student support plans to align with Department of Education requirements. | Learning specialist(s) | -1% |
| Task 5 | Establish a structured approach and clear expectations for school-wide student surveys to ensure consistent and reliable data collection. | Leadership team Teacher(s) | -1% |

Monitoring and assessment - 2026

Mid Term 3 monitoring

| ### Goal 1 | To improve student learning outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 1.c | Build staff capability to analyse and use learning and wellbeing data to accurately determine student’s needs |  |  |
| Actions | Build a data-driven culture by providing targeted professional development, implementing consistent assessment and wellbeing tracking tools, facilitating regular data review meetings, and supporting teachers through coaching and collaboration to use insights for informed instruction and student support. |  |  |
| Delivery of the annual actions for this KIS |  |  |  |
| Evidence of change | -Targeted Professional Learning: Provide professional development for teachers and leadership focused on data literacy, assessment interpretation, and wellbeing monitoring to build staff capability in analysing and using student data. - Expected Staff Outcomes: Teachers will demonstrate increased knowledge and skills in interpreting data, making evidence-based decisions, and applying differentiated strategies to support student learning and wellbeing. - Structured Data Meetings: Embed regular team and year-level meetings with agendas, minutes, and action plans to collaboratively identify student needs and plan interventions. - Consistent Assessment & Tracking Tools: Use platforms and tools such as Essential Assessment, PAT, Dibels, SPAKLE online tracking, internal School Tracking Documents, and Compass to collect, monitor, and report on student progress. - Data-Informed Planning: Teachers will routinely integrate data into lesson planning, make timely instructional adjustments, and provide targeted support for individual and group student needs. - Ongoing Coaching & Peer Support: Implement coaching, peer observations, and PLC reflections to reinforce collaborative decision-making, evidence-based practices, and a school-wide culture of data-informed practice. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Professional Learning & Training • Attendance records from data literacy or assessment-focused professional development sessions. • Workshop agendas, presentations, and resources showing the focus on interpreting learning and wellbeing data. • Teacher reflections or feedback forms demonstrating improved understanding of data use. | Leadership team | -1% |
| Task 2 | Structured Data Meetings • Meeting agendas and minutes documenting discussion of student data and decisions about targeted support. • Action plans created from data discussions identifying student learning and wellbeing needs. • Records showing follow-up on agreed strategies and interventions. | Leadership team | -1% |
| Task 3 | Assessment & Tracking Tools • Reports from platforms (e.g., Essential Assessment, Compass, NAPLAN, or internal tracking spreadsheets) showing student performance and wellbeing trends. • Evidence of consistent entry of assessment and wellbeing data by teachers. • Dashboards or visual summaries used to inform teaching practice. | Teacher(s) Leadership team | -1% |
| Task 4 | Data-Informed Planning • Lesson plans and unit plans explicitly linked to student data and differentiated strategies. • Examples of interventions or programs implemented in response to data analysis. • Evidence of student progress monitored over time using formative and summative assessments | Teacher(s) | -1% |
| Task 5 | Ongoing Coaching & Peer Support • Coaching logs showing sessions focused on interpreting and applying data. • Peer observation notes or PLC reflections highlighting the use of data to inform instruction. • Staff surveys or feedback demonstrating increased confidence in using data to identify student needs. | Teacher(s) Leadership team | -1% |

| ### Goal 2 | To improve student wellbeing outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 2.b | Review and embed a whole school positive approach to wellbeing. |  |  |
| Actions | Strengthen Sebastopol Primary School’s whole-school wellbeing approach by refining documentation, systems, and processes, enhancing the Wellbeing Hub, implementing Positive Classroom Management Strategies with ongoing professional learning, clarifying wellbeing team roles, and using student data to guide timely, targeted support and reintegration strategies. |  |  |
| Delivery of the annual actions for this KIS |  |  |  |
| Evidence of change | - Reduce behaviour referrals and student suspensions. - Increase positive outcomes in the Attitudes to School Survey. - Ensure consistent implementation and regular review of student support plans, including Individual Education Plans, Behaviour Support Plans and Safety Plans. - Fully implement the Positive Classroom Management Strategies, including refinement of the Behaviour Matrix and Behaviour Flowcharts. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Develop clear role descriptions for Wellbeing Team members. | Principal Learning specialist(s) Mental health and wellbeing leader Disability inclusion coordinator | -1% |
| Task 2 | Implement PCMS peer observations across Terms 2, 3 and 4. | Learning specialist(s) Teacher(s) Principal | -1% |
| Task 3 | Refresh the Wellbeing Hub and clarify associated expectations. | All staff Learning specialist(s) Mental health and wellbeing leader Principal | -1% |
| Task 4 | Update student support plans to align with Department of Education requirements. | Learning specialist(s) | -1% |
| Task 5 | Establish a structured approach and clear expectations for school-wide student surveys to ensure consistent and reliable data collection. | Leadership team Teacher(s) | -1% |

Monitoring and assessment - 2026

Mid Term 4 monitoring

| ### Goal 1 | To improve student learning outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 1.c | Build staff capability to analyse and use learning and wellbeing data to accurately determine student’s needs |  |  |
| Actions | Build a data-driven culture by providing targeted professional development, implementing consistent assessment and wellbeing tracking tools, facilitating regular data review meetings, and supporting teachers through coaching and collaboration to use insights for informed instruction and student support. |  |  |
| Delivery of the annual actions for this KIS |  |  |  |
| Evidence of change | -Targeted Professional Learning: Provide professional development for teachers and leadership focused on data literacy, assessment interpretation, and wellbeing monitoring to build staff capability in analysing and using student data. - Expected Staff Outcomes: Teachers will demonstrate increased knowledge and skills in interpreting data, making evidence-based decisions, and applying differentiated strategies to support student learning and wellbeing. - Structured Data Meetings: Embed regular team and year-level meetings with agendas, minutes, and action plans to collaboratively identify student needs and plan interventions. - Consistent Assessment & Tracking Tools: Use platforms and tools such as Essential Assessment, PAT, Dibels, SPAKLE online tracking, internal School Tracking Documents, and Compass to collect, monitor, and report on student progress. - Data-Informed Planning: Teachers will routinely integrate data into lesson planning, make timely instructional adjustments, and provide targeted support for individual and group student needs. - Ongoing Coaching & Peer Support: Implement coaching, peer observations, and PLC reflections to reinforce collaborative decision-making, evidence-based practices, and a school-wide culture of data-informed practice. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Professional Learning & Training • Attendance records from data literacy or assessment-focused professional development sessions. • Workshop agendas, presentations, and resources showing the focus on interpreting learning and wellbeing data. • Teacher reflections or feedback forms demonstrating improved understanding of data use. | Leadership team | -1% |
| Task 2 | Structured Data Meetings • Meeting agendas and minutes documenting discussion of student data and decisions about targeted support. • Action plans created from data discussions identifying student learning and wellbeing needs. • Records showing follow-up on agreed strategies and interventions. | Leadership team | -1% |
| Task 3 | Assessment & Tracking Tools • Reports from platforms (e.g., Essential Assessment, Compass, NAPLAN, or internal tracking spreadsheets) showing student performance and wellbeing trends. • Evidence of consistent entry of assessment and wellbeing data by teachers. • Dashboards or visual summaries used to inform teaching practice. | Teacher(s) Leadership team | -1% |
| Task 4 | Data-Informed Planning • Lesson plans and unit plans explicitly linked to student data and differentiated strategies. • Examples of interventions or programs implemented in response to data analysis. • Evidence of student progress monitored over time using formative and summative assessments | Teacher(s) | -1% |
| Task 5 | Ongoing Coaching & Peer Support • Coaching logs showing sessions focused on interpreting and applying data. • Peer observation notes or PLC reflections highlighting the use of data to inform instruction. • Staff surveys or feedback demonstrating increased confidence in using data to identify student needs. | Teacher(s) Leadership team | -1% |

| ### Goal 2 | To improve student wellbeing outcomes. |  |  |
| --- | --- | --- | --- |
| ### KIS 2.b | Review and embed a whole school positive approach to wellbeing. |  |  |
| Actions | Strengthen Sebastopol Primary School’s whole-school wellbeing approach by refining documentation, systems, and processes, enhancing the Wellbeing Hub, implementing Positive Classroom Management Strategies with ongoing professional learning, clarifying wellbeing team roles, and using student data to guide timely, targeted support and reintegration strategies. |  |  |
| Delivery of the annual actions for this KIS |  |  |  |
| Evidence of change | - Reduce behaviour referrals and student suspensions. - Increase positive outcomes in the Attitudes to School Survey. - Ensure consistent implementation and regular review of student support plans, including Individual Education Plans, Behaviour Support Plans and Safety Plans. - Fully implement the Positive Classroom Management Strategies, including refinement of the Behaviour Matrix and Behaviour Flowcharts. |  |  |
| Progress of evidence of change for this KIS |  |  |  |
| Enablers |  |  |  |
| Barriers |  |  |  |
| OPTIONAL: Upload evidence |  |  |  |
| Tasks | Task | Who | Percentage Complete |
| Task 1 | Develop clear role descriptions for Wellbeing Team members. | Principal Learning specialist(s) Mental health and wellbeing leader Disability inclusion coordinator | -1% |
| Task 2 | Implement PCMS peer observations across Terms 2, 3 and 4. | Learning specialist(s) Teacher(s) Principal | -1% |
| Task 3 | Refresh the Wellbeing Hub and clarify associated expectations. | All staff Learning specialist(s) Mental health and wellbeing leader Principal | -1% |
| Task 4 | Update student support plans to align with Department of Education requirements. | Learning specialist(s) | -1% |
| Task 5 | Establish a structured approach and clear expectations for school-wide student surveys to ensure consistent and reliable data collection. | Leadership team Teacher(s) | -1% |

Monitoring and Self-assessment - 2026

SEIL Feedback

Submitted Feedback

Congratulations Kane and the Sebastopol PS Team for a very busy and productive semester. Is great to hear about the steady improvement underway, and you have identified key areas in both learning and wellbeing where the future focus will lie. Your connection to the school is strong Kane and it has been great to watch you make your mark. Exciting times ahead. Below is a summary of your comments from our mid-cycle AIP conversation. This semester, there has been a deliberate shift in the Learning Specialist role to focus more directly on what is happening in classrooms. While earlier work had concentrated on planning, scope and sequence, there had been limited opportunity for genuine collaboration with staff. In Term 1, this changed, with a stronger emphasis on constructing planning approaches alongside teachers and using data more actively in planning conversations, supported by the Learning Specialist and Principal. Planning and enabling learning have been the key focus areas, and staff involvement in self-assessment has helped build greater ownership of this work. As a result, both areas have moved from emerging to evolving. Reading has been a particular PLC focus, and professional learning has also included Education Support staff, helping to strengthen a more consistent whole-school approach. The work around opportunities to respond, supported through coaching, has been especially positive. Even experienced teachers, who had previously made limited use of these strategies, are showing growth in this area, and this is contributing to stronger classroom practice. A real strength of the school is the way teaching and learning remain a clear priority while still responding to the needs of the community. Leadership alignment has been important here, with the Assistant Principal and Mental Health and Wellbeing Leader working closely together. This has supported the development of the wellbeing hub as a structured space for reset and regulation, accessed either through planned supports or identified need during the day. Strategies such as Zones of Regulation and a range of movement and calming activities are helping students regulate more effectively and return to learning. Our work has been strengthened by support from our PCMS Coach and from professional learning with Glenn Pearsall. The school has also responded to growing enrolments and increasing complexity, including a large number of DIPs in progress, by using funding to reduce class sizes and add two additional classes in Semester 2. Overall, the school is making steady progress, with stronger alignment between planning, wellbeing and classroom practice, and a clearer foundation for continued improvement. Submitted by Anne Gawith (SEIL) on 01 July, 2026 at 02:59 PM